## Sheet1
Sprint no. | Story points | Hours Taken | Team Velocity
1 | 58 | 21 | 2.8 story/hour
2 | 29 | 10 | 2.9 story/hour
4 | 52 | 20 | 2.6 story/hour
I=1.035
Estimated Team Velocity for Sprint 5 = 2.6*1.035 =2.7 story/hour