## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As an unregistered user I should be able to register online to have full access to features | 3 | Karim Serry | Mariam | Emad
1.1 | As a registered user/admin I should be able to update/delete my profile to be up to date. | 5 | Karim Serry | Mariam | Emad
1.2 | As an admin I can send emails to all subscribers to keep them updated. | 3 | Mariam Walid | Emad | Karim
1.3 | As an admin I can delete any subscriber to filter spams. | 2 | Mariam Walid | Emad | Karim
1.4 | As a user I can subscribe to mailing list to be updated. | 2 | Mariam Walid | Emad | Karim
1.5 | As an admin I can create/update/delete any participating club on the hub to be up to date. | 3 | Mariam Walid | Emad | Karim
1.6 | As a user I can send contact forms to MUN to leave any inquiry. | 2 | Mariam Walid | Emad | Karim
1.7 | As an admin I can create/update/delete any page that belongs to any of MUN councils. | 8 | Emad | Moaz | Mariam
1.8 | As an admin I can create/update/delete any event. | 8 | Moaz | Omar | Karim
1.9 | As an admin I can create/update/delete any announcement to keep the users up to date. | 5 | Kandil | Aly | Ziad
2 | As an admint I can create/update/delete any FAQ to keep the users more aware of the website. | 5 | Ziad | Kandil | Aly
2.1 | As an admin I can create/update/delete any product to keep the users up to date with what MUN sells. | 8 | Omar | Mariam | Emad
2.2 | As an admin I should be able to add/delete any academic paper from the portal library to keep it up to date | 8 | Aly | Ziad | Kandil