## Sheet1
Unique ID | User story | Story Points | Depends on | Assignee | Testing User Story?
1 | As a User I should be able to register to access the Hub( create my profile ) | 3 |  | Kareem Serry | none
1.1 | As an AWG-Admin I should be able to edit the user database to maintain balance in the hub( create , delete , read , edit ) | 1 | 1 | Kareem Serry | none
1.2 | As a User I should be able to edit my profile to keep it up to date | 2 | 1 | Kareem Serry | same assignee
1.3 | As a User I should be able to visit other users profiles to view my profile | 1 | 1 | Kareem Serry | same assignee
1.4 | As a User I should be able to remove my account to stop using this service(delete my profile) | 1 | 1 | Kareem Serry | same assignee
2 | As an AWG-admin I should be able to add, edit and delete FAQs to keep the most relevant ones | 5 | 2.2 | Ziad Mostafa | none
2.1 | As a user I should be able to view FAQs | 1 | 2 | Ziad Mostafa | same assignee
2.2 | As a user I could add a question on FAQs | 1 |  | Ziad Mostafa | same assignee
3 | As a an MUN-admin I should be able to add,edit and delete announcements to keep the announcements up to date. | 5 |  | Youssef Kandil | none
3.1 | As a user I should be able to view announcements to stay up to date. | 1 | 3 | Youssef Kandil | same assignee
4 | As an admin I should be able to add, edit and delete Library portal entries to keep them up to date. | 5 |  | Aly Mohamed | none
4.1 | As a user I should be able to view Library portal entries to retrieve academic papers. | 1 | 4 | Aly Mohamed | same assignee
5 | As a council/office/committee head I should be able to assign members to my council/office to keep the roster updated. | 2 |  | Ahmed Emad | none
5.1 | As a council/office/committee head I should be able to edit(update/delete) my council/office description or (Event if available) to keep it up to date. | 2 | 5 | Ahmed Emad | same assignee
5.2 | As a user I should be able to retrieve(view) council/office members and description to learn more about them. | 1 | 5 | Ahmed Emad | same assignee
5.3 | As a council/office/committee head I should be able to assign/delete/add roles to lower access members | 1 | 1,5 | Ahmed Emad | same assignee
6 | As an admin I should be able to add,edit and delete events to keep them up to date. | 5 |  | Omar Hussein | none
6.1 | As a user I should be able to view events to stay up to date. | 1 | 6 | Omar Hussein | same assignee
7 | As an admin I should be able to add,edit and delete merchandise to keep it up to date. | 5 |  | Mariam Walid | none
7.1 | As a user I should be able to view merchandise to learn more about it. | 1 | 7 | Mariam Walid | same assignee
8 | As an admin I should be able to edit , view and delete the mailing list to keep it relevant. | 3 |  | Moaz Kassab | none
8.1 | As a user I should be able to subscribe (add my mail) / unsubscribe(delete my mail) to/from the mailing list to stay up to date. | 2 | 8 | Moaz Kassab | same assignee
10 | As User I should be able to create , edit , delete a feedback on any Event | 3 | 6 | Omar Hussein | none
10.1 | As User I should be able to view a feedback on any Event | 1 | 6 | Omar Hussein | same assignee