## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a user I should be able to view my profile when I am logged in. | 5 | Kareem Serry | Emad | Mariam
1.1 | As User I should be able to view products/merchandise to know what MUN provides. | 5 | Omar hussein | Ali | Ziad
1.2 | As User I should be able to view FAQs to answer any questions I have. | 5 | Ziad Mustafa | Moaz | Kareem
1.3 | As a user I should be able to view academic papers in portal library to check specific articles. | 5 | Ali Mohamed | Youssef | Ziad
1.4 | As User I should be able to view upcoming and previous events to be updated. | 5 | Moaz kassab | Omar | Emad
1.5 | As User I should be able to view councils/offices to know what they have been up to. | 5 | Ahmed Emad | Kareem | Youssef
1.6 | As User I should be able to view clubs to know what clubs are participating. | 3 | Mariam Walid | Moaz | Ali
1.7 | As an MUN Admin I should be able to view subscribers for mailing service. | 3 | Mariam Walid | Emad | Omar
1.8 | As User I should be able to view announcements to know latest news. | 5 | Youssef Kandil | Ziad | Moaz
1.9 | As a user I should be able to view MUN's page. | 3 | Omar hussein | Kareem | Ali
2 | As a user I should see events timeline to be updated. | 3 | Moaz kassab | Mariam | Emad
2.1 | As a user I should see about us section to know MUN's mission , mission and achievement. | 1 | Mariam Walid | Emad | Ali
2.2 | As a user I should be able to fill contact us form to inquire about anything in MUN. | 1 | Mariam Walid | Emad | Ali
2.3 | As a user I should be able to login/ logout to my profile. | 3 | Kareem Serry | Emad | Moaz